## Timetable
Task | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  | December |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  |  | May
1 | Design and draft survey | 1: Start up meeting
2 | Physical design & print | 8: Design; 10: Print
3 | Design and hosting of an online version of the survey | 8: Design; 13: Hosting
4 | Printing, Distribution and collection of paper surveys | 9: Printing, publicising; 13: Distribution, collection
5 | On the ground consultations | bar: 12 to 17
6 | Input of paper returns & analysis | bar: 15 to 19
7 | Extracting data from online submissions | bar: 18 to 19
8 | Producing a summary analysis and presentation | 21: Draft; 22: Final
9 | Producing Plan | bar: 23 to 26

## Stakeholders
|  | Written methods |  |  |  | Visual methods |  | IT based |  |  | Street stalls/stands | One to one interviews |  | Drama/art
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Stakeholders | Online questionnaire | Paper questionnaire | Postcard with quick questions | Book of Stories | Timeline | Picture vision | Interactive website | Twitter, Facebook etc | Phone apps | At events, market days; ratify early findings | Street interviews. | Phone interviews | Forum theatre/community artist
1 | Working age
2 | Older
3 | Children
4 | Young people
5 | Businesses
6 | Farmers
7 | Landowners
8 | Public bodies
9 | Vol groups