## Sheet1
Bayston Hill Community Led Plan 2016
|  |  | 2015 | [9 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
Timeline |  | Month | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | june | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | june | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | june | July | Aug | Sep | Oct | Nov | Dec
|  | Plan period number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46
Action
Launch Plan Revision | bar: 2015 Mar 1
Convene initial consultation meetings | bar: 2015 Apr 2
Identify core steering group | bar: 2015 May 3
Adopt constitution | bar: 2015 May 3
Appoint officers | bar: 2015 May 3
Develop outline approach | bar: 2015 June 4
Develop work stream themes | bar: 2015 Sep 7 to 2015 Oct 8
Establish work stream leads | bar: 2015 Nov 9
Develop workstream plans | bar: 2016 Apr 14 to 2016 May 15
Recruit workstream volunteers | bar: 2016 May 15 to 2016 june 16
Workstream lead training events | bar: 2016 june 16
Comms strategy developed and agreed | bar: 2016 May 15
Consultation:
Work stream stakeholder consultation | bar: 2016 July 17 to 2016 Nov 21
Work stream events | bar: 2016 Sep 19 to 2016 Nov 21
Work stream focused surveys and polling | bar: 2016 Sep 19 to 2016 Nov 21
Work stream message collation | bar: 2016 Dec 22 to 2017 Feb 24
Development of wider survey
Work with consultants on question design | bar: 2016 Nov 21 to 2017 Feb 24
Work stream and Steering group awayday with consultants | bar: 2016 Dec 22
First draft of questionnaire circulated | bar: 2017 Feb 24 to 2017 Mar 25
Feedback consolidation from work groups | bar: 2017 Mar 25
Second Draft submitted to Parish Council for comment | bar: 2017 Apr 26
Questionnaire signed off | bar: 2017 May 27
Questionnaire published and circulated | bar: 2017 june 28 to 2017 Aug 30
awareness raising comms | bar: 2017 june 28 to 2017 Aug 30
Statutory stakeholder consultation/engagement | bar: 2017 Apr 26 to 2017 Aug 30
events:
breakfast meetings | bar: 2017 june 28 to 2017 July 29
public meetings | bar: 2016 Sep 19; 2017 July 29; 2018 Aug 42
social media polling/discussion | bar: 2016 Nov 21 to 2017 Jan 23; 2017 Apr 26 to 2017 May 27; 2017 Aug 30
Collation of survey results | bar: 2017 Sep 31
Analysis by consultants | bar: 2017 Oct 32 to 2017 Nov 33
Feedback from consultants | bar: 2017 Nov 33 to 2017 Dec 34
Analysis of feedback and messaging by steering group | bar: 2018 Jan 35 to 2018 Feb 36
Conversion of feedback analysis to plan based narrative and outcomes | bar: 2018 Feb 36 to 2018 Mar 37
Write Draft plan | bar: 2018 Mar 37 to 2018 Apr 38
consultation with Parish, CET and others | bar: 2018 Apr 38 to 2018 May 39
Circulate first draft | bar: 2018 May 39
Revisions | bar: 2018 june 40
Finalise second draft | bar: 2018 june 40 to 2018 July 41
Steering group conference/away day to agree final draft | bar: 2018 July 41
Submit final draft to PC | bar: 2018 July 41
publication and circulation | bar: 2018 Aug 42 to 2018 Sep 43
On going tasks
Progress reporting to Parish Council | bar: 2016 Apr 14; 2016 june 16; 2016 Sep 19; 2016 Nov 21; 2017 Jan 23; 2017 Mar 25; 2017 May 27; 2017 July 29; 2017 Sep 31; 2017 Nov 33; 2018 Jan 35; 2018 Mar 37; 2018 May 39; 2018 July 41
Progress reporting to village residents
Web site design | bar: 2016 May 15
Website live | bar: 2016 june 16
wider comms messages | bar: 2016 Aug 18 to 2016 Oct 20; 2017 Feb 24 to 2017 Apr 26; 2017 june 28 to 2017 Aug 30; 2017 Nov 33 to 2018 Feb 36; 2018 june 40 to 2018 Sep 43
formal ongoing Consultation with Shropshire Council - key times | bar: 2016 Apr 14; 2016 Dec 22 to 2017 Feb 24; 2017 May 27; 2017 Nov 33 to 2017 Dec 34; 2018 Apr 38 to 2018 Sep 43
Consultation with neighbouring parishes | bar: 2016 Sep 19 to 2016 Nov 21; 2017 Dec 34 to 2018 Jan 35
Awareness/tracking of developing planning law
milestones
activities
sponsor progress
supporting activities (many continuous)
ongoing background activty